Cross-Sell Lead Generation

Pod Architecture & Implementation Plan

Document 3 of 4

Version 1.0 | February 2026

Table of Contents

# Introduction

This document details the pod-based development architecture for the Next Best Product cross-sell system. The modular approach enables parallel development, faster delivery, and specialized team focus. Six independent pods build components that integrate through well-defined interfaces.

## Pod Architecture Benefits

- Parallel Development: Multiple teams work simultaneously, reducing overall timeline

- Specialization: Teams focus on areas of expertise (ML, event detection, data engineering)

- Independence: Pods can progress without blocking each other

- Phased Delivery: Early pods deliver value while later pods continue development

- Risk Mitigation: Issues in one pod don't cascade to others

# Pod Overview

| Pod | Team | Duration | Start | Dependencies | Status |
| --- | --- | --- | --- | --- | --- |
| Pod 5: Data | 2-3 eng | 4-6 wk | Week 0 | None | Partial |
| Pod 1: Adjacency | 1-2 eng | 3-4 wk | Week 1 | Pod 5 | Not started |
| Pod 2: Propensity | 2-3 DS+1 MLE | 10-12 wk | Week 1 | Pod 5 | Not started |
| Pod 3: Events | 2-3 eng | 12-16 wk | Week 1 | Pod 5 | Not started |
| Pod 4: Competitive | 2 eng | 8-10 wk | Week 1 | Pod 5 | 60-70% |
| Pod 0: Orchestration | 2-3 eng | 8-10 wk | Week 6-8 | Pods 1-4 | Not started |

Total Team Size: 12-16 people

Total Duration: 16-20 weeks to full system

First Delivery: Week 8 (MVP with Pods 1, 4, 5, and basic Pod 0)

# Pod Detailed Specifications

## Pod 0: Orchestration & Scoring Engine

### Responsibilities

- Master scoring formula combining all tier outputs

- Product ranking logic per customer

- Lead package generation (talking points, conversion probability, revenue estimates)

- Lead routing rules (which BDO gets which lead based on territory/specialization)

- Integration layer with all other pods

- API/service layer for downstream systems (CRM, dashboards)

### Key Deliverables

- Next best product scoring service (REST API)

- Daily batch lead generation process

- Talking points generation engine

- Lead routing and distribution system

- Performance monitoring dashboards

### Technical Stack

- Python for scoring logic

- Pandas/NumPy for data manipulation

- PostgreSQL or similar for lead storage

- FastAPI or Flask for REST API

- Airflow or similar for batch orchestration

## Pod 1: Adjacency Engine

### Responsibilities

- Product relationship matrix definition and maintenance

- Adjacency scoring rules (0-100 per product pair)

- Timing filters (when to offer, when to wait based on tenure/lifecycle)

- Product profitability weighting

### Key Deliverables

- Adjacency scoring function/API

- Timing filter function/API

- Product adjacency lookup matrix (JSON or database table)

- Documentation of all product relationships and timing rules

### Technical Stack

- Python or SQL for rules engine

- JSON or database for rule storage

- Simple REST API for scoring

## Pod 2: Propensity Models

### Responsibilities

- Feature engineering pipeline from raw transaction data

- Product-specific ML models (one per major product)

- Model training, validation, hyperparameter tuning

- Model deployment to production

- Model performance monitoring and retraining

- Batch scoring infrastructure

### Key Deliverables

- Propensity scoring function/API (returns 0.0-1.0 probability)

- Model artifacts (trained models, feature transformers)

- Model performance metrics and monitoring

- Feature importance analysis

- Retraining pipeline

### Technical Stack

- Python (scikit-learn, XGBoost, LightGBM)

- MLflow or similar for model management

- Feature store (Feast or custom)

- Model serving (MLflow, TensorFlow Serving, or custom API)

## Pod 3: Event Detection

### Responsibilities

- Transaction pattern signatures for 10+ life events

- Real-time or daily event detection from transaction streams

- Confidence scoring for detected events

- Event catalog expansion and refinement

- Merchant categorization and text parsing

### Key Deliverables

- Event detection function/API (returns event type, confidence, evidence)

- Event boost multiplier function (1.0-10.0 based on relevance)

- Real-time event alerts for urgent leads

- Event catalog documentation

### Technical Stack

- Python for pattern matching

- Regex and NLP libraries for transaction description parsing

- Real-time streaming (Kafka/Kinesis) or batch processing

- Alert system for high-confidence events

## Pod 4: Competitive Displacement

### Responsibilities

- External relationship detection from payment patterns

- Loan term estimation (reverse engineer from monthly payments)

- Competitive rate intelligence gathering and maintenance

- Savings calculation and competitive offer generation

### Key Deliverables

- External relationship detection function/API

- Competitive offer generation with quantified savings

- Competitive boost multiplier function (1.0-10.0)

- Market rate database and update process

### Technical Stack

- Python for payment pattern recognition

- Financial calculation libraries for loan term estimation

- Database for market rate storage

- API for offer generation

### Current Status

60-70% complete based on existing external relationship detection work. Remaining work: loan term estimation algorithms, competitive offer generation, savings calculators.

## Pod 5: Data Foundation

### Responsibilities

- ETL pipelines from source systems (Core Banking, CRM, Card Processor)

- Data quality monitoring and cleansing

- Customer-product relationship table (who has what)

- Transaction history aggregation and storage

- Feature store for pre-computed ML features

- Market data feeds integration

### Key Deliverables

- Customer product holdings data mart

- Transaction history database (6-12 months per customer)

- Customer profile data mart

- Market rates feed

- Data quality dashboards

- Data APIs for all pods

### Technical Stack

- SQL (for data marts)

- Python (for ETL)

- Airflow or similar (for pipeline orchestration)

- Data warehouse (Snowflake, Redshift, or on-prem)

- dbt (for data transformations)

# Implementation Timeline

## Week-by-Week Gantt Chart

Pod 5 (Data Foundation):

  - Week 0-3: Core pipeline development

  - Week 4-6: Data quality implementation

  - Week 6+: Ongoing maintenance and enhancement

Pod 1 (Adjacency):

  - Week 1-2: Matrix design workshop and documentation

  - Week 3-4: Rules engine build and testing

  - Week 4+: Integration with Pod 0, ongoing rule refinement

Pod 2 (Propensity):

  - Week 1-4: Feature engineering and first model (Credit Card)

  - Week 5-8: Second and third models (Auto, Personal Loan)

  - Week 9-12: Remaining models and deployment

  - Week 12+: Monitoring, retraining, expansion

Pod 3 (Events):

  - Week 1-4: Top 3 events (Home Purchase, Baby, Business)

  - Week 5-8: Next 3 events (Job Change, Vehicle, Renovation)

  - Week 9-12: Next 4 events (Tuition, Windfall, Retirement, Divorce)

  - Week 13-16: Refinement and edge cases

Pod 4 (Competitive):

  - Week 1-4: Enhance existing detection, add term estimation

  - Week 5-8: Build offer generation and savings calculators

  - Week 8+: Integration with Pod 0

Pod 0 (Orchestration):

  - Week 6-8: Design and architecture

  - Week 9-12: Build master scoring and integration

  - Week 13-16: Lead generation, routing, CRM integration

# Integration & Communication

## Pod Communication Cadence

- Weekly Pod Sync (30 min): Each pod shares progress, blockers escalated

- Bi-weekly Cross-Pod Integration (1 hour): End-to-end flow testing

- Monthly Steering Committee: Demo progress to stakeholders, adjust priorities

## API Contracts Between Pods

All scoring pods (1-4) expose standardized functions to Pod 0:

  - get_score(customer_id, product): Returns numerical score/probability

  - get_context(customer_id, product): Returns explanatory details/evidence

  - get_talking_points(customer_id, product): Returns BDO conversation starters

Pod 5 exposes data APIs to all pods:

  - get_customer_products(customer_id): Returns list of current products

  - get_transaction_history(customer_id, days): Returns transaction data

  - get_customer_profile(customer_id): Returns demographics, tenure

# Deployment Phases

## Phase 1: MVP (Week 8)

Components Ready: Pod 5 (data), Pod 1 (adjacency), Pod 4 (competitive), basic Pod 0

Capability: Simple adjacency-based leads + competitive displacement

Pilot: 10 BDOs, single product focus (Auto Loan Refi)

## Phase 2: Enhanced (Week 12)

Components Ready: Add Pod 2 (first 2-3 propensity models), Pod 3 (top 6 events)

Capability: Scored leads with probabilities, event-triggered alerts

Scale: 50 BDOs, 3 products

## Phase 3: Full System (Week 16)

Components Ready: All pods complete, full Pod 0 orchestration

Capability: Complete Next Best Product engine

Scale: All BDOs, all products

## Phase 4: Optimization (Week 20+)

Activities: A/B testing, model refinement, new features

# Success Criteria by Pod

## Pod 5 (Data Foundation)

- Data pipeline uptime > 99%

- Data latency < 24 hours from source to data mart

- Data quality score > 95%

- API response time < 100ms

## Pod 1 (Adjacency)

- Product matrix covers 100% of product pairs

- Timing rules defined for all delayed offers

- API response time < 50ms

## Pod 2 (Propensity)

- Model AUC-ROC > 0.70 for each product

- Top decile lift > 3x

- Model refresh cycle: Monthly scoring, quarterly retraining

## Pod 3 (Events)

- Detect 10+ event types

- False positive rate < 20%

- Event detection latency < 24 hours

## Pod 4 (Competitive)

- Detect 5+ external product types

- Savings calculations within 10% of actual

- Confidence scoring accuracy > 80%

## Pod 0 (Orchestration)

- Daily batch processing < 2 hours for full customer base

- API availability > 99.5%

- Lead generation accuracy (correct recommendations) > 85%

# Appendix: Related Documents

This Pod Architecture & Implementation Plan is Document 3 of 4:

- Document 1: Executive Summary & Strategic Overview

- Document 2: Four-Tier Intelligence Framework

- Document 3: Pod Architecture & Implementation Plan (this document)

- Document 4: BDO Operational Guide